## Sheet1
Serial | Task Name | Planned Efford | Completed | Actual Efford
1 | Identify stakeholders (patients, doctors, hospitals, admin) | 2 | Yes | 2
2 | Gather functional requirements (appointments, bed booking, AI chat) | 2 | Yes | 2
3 | Gather non-functional requirements (security, scalability, usability) | 2 | Yes | 3
4 | Define use cases and user roles | 1 | Yes | 1
5 | Prepare PRD | 3 | Yes | 2 | BAC | 142
6 | Review and validate requirements with stakeholders | 3 | Yes | 3 | BCWS | 76
7 | Create initial product backlog in Trello | 3 | Yes | 3 | BCWP | 61
8 | Define system architecture (client-server, APIs) | 3 | Yes | 4 | ACWP | 63
9 | Create database schema (ER diagram) | 4 | Yes | 2
10 | Design UI/UX wireframes for patient/doctor/hospital apps | 3 | Yes | 3
11 | Define API endpoints and integration plan | 4 | Yes | 4 | SPI | 0.80263
12 | Plan AI Doctor module architecture | 5 | Yes | 5 | SV | -15
13 | Design admin panel structure with reporting tools | 2 | Yes | 2 | CPI | 0.96825
14 | Review and finalize system design document | 3 | Yes | 4 | CV | -2
15 | Develop user authentication (signup, login, JWT security) | 4 | Yes | 3
16 | Implement patient profile management | 3 | Yes | 4 | Sechdule for Completetion | 53.5211 | %
17 | Implement doctor search and appointment booking | 2 | Yes | 3 | Complete | 42.9577 | %
18 | Develop hospital bed booking feature | 3 | Yes | 4
19 | Implement test ordering system | 2 | Yes | 3
20 | Develop patient–doctor chat interface | 2 | Yes | 2
21 | Integrate payment gateway (if applicable) | 5 | Yes | 4
22 | Review and test patient module features | 4 | No
23 | Develop doctor profile management | 3 | No
24 | Implement appointment scheduling and management | 3 | No
25 | Create blog posting and review feature | 2 | No
26 | Integrate chat with patients | 3 | No
27 | Add hospital collaboration functionality | 4 | No
28 | Review and test doctor module features | 4 | No
29 | Implement hospital registration and profile management | 3 | No
30 | CRUD for hospital equipment and test services | 2 | No
31 | Manage patient requests (accept/reject system) | 3 | No
32 | Develop hospital–doctor linking | 4 | No
33 | Review and test hospital module features | 3 | No
34 | Implement admin login and authentication | 3 | No
35 | Manage users (patients, doctors, hospitals) | 2 | No
36 | Add reporting & graphs dashboard | 3 | No
37 | Implement audit logs and monitoring | 4 | No
38 | Develop symptom input form (NLP interface) | 2 | No
39 | Train/integrate AI model for basic diagnosis suggestions | 3 | No
40 | Test AI responses for accuracy & safety | 3 | No
41 | Unit testing for all modules | 3 | No
42 | Integration testing (patient–doctor–hospital flow) | 3 | No
43 | User Acceptance Testing (UAT) with stakeholders | 4 | No
44 | Bug fixing and retesting | 2 | No
45 | Deploy system to cloud/hosting server (CI/CD setup) | 3 | No
46 | Publish app (mobile/web) and provide user documentation | 5 | No
47 | Plan maintenance, updates, and future scalability | 3 | No
142