## Sheet1
Serial No. | Task Name | User Type | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | W25 | W26
1 | Identify stakeholders (patients, doctors, hospitals, admin) | Mahbub Hasan | bar: Week 1
2 | Gather functional requirements (appointments, bed booking, AI chat) | Mujtahid Tabassum | bar: Week 1
3 | Gather non-functional requirements (security, scalability, usability) | MD. Zobayer Hosen | bar: Week 1
4 | Define use cases and user roles | Tauhidul Islam | bar: Week 2
5 | Prepare PRD | Mujtahid Tabassum | bar: Week 2
6 | Review and validate requirements with stakeholders | Mahbub Hasan | bar: Week 5
7 | Create initial product backlog in Trello | Tauhidul Islam | bar: Week 7
8 | Define system architecture (client-server, APIs) | MD. Zobayer Hosen | bar: Week 8
9 | Create database schema (ER diagram) | Mujtahid Tabassum | bar: Week 8
10 | Design UI/UX wireframes for patient/doctor/hospital apps | Mahbub Hasan | bar: Week 8
11 | Define API endpoints and integration plan | Tauhidul Islam | bar: Week 3
12 | Plan AI Doctor module architecture | MD. Zobayer Hosen | bar: Week 3
13 | Design admin panel structure with reporting tools | Mahbub Hasan | bar: Week 4
14 | Review and finalize system design document | Mujtahid Tabassum | bar: Week 8
15 | Develop user authentication (signup, login, JWT security) | Tauhidul Islam | bar: Week 6 to Week 8
16 | Implement patient profile management | MD. Zobayer Hosen | bar: Week 9
17 | Implement doctor search and appointment booking | Mahbub Hasan | bar: Week 9
18 | Develop hospital bed booking feature | Mujtahid Tabassum | bar: Week 10
19 | Implement test ordering system | Tauhidul Islam | bar: Week 10
20 | Develop patient–doctor chat interface | MD. Zobayer Hosen | bar: Week 11 to Week 12
21 | Integrate payment gateway (if applicable) | Mahbub Hasan | bar: Week 12
22 | Review and test patient module features | Mujtahid Tabassum | bar: Week 13
23 | Develop doctor profile management | Tauhidul Islam | bar: Week 13 to Week 14
24 | Implement appointment scheduling and management | MD. Zobayer Hosen | bar: Week 14 to Week 16
25 | Create blog posting and review feature | Mahbub Hasan | bar: Week 16 to Week 17
26 | Integrate chat with patients | Mujtahid Tabassum | bar: Week 13 to Week 14
27 | Add hospital collaboration functionality | Tauhidul Islam | bar: Week 13 to Week 14
28 | Review and test doctor module features | MD. Zobayer Hosen | bar: Week 13 to Week 14
29 | Implement hospital registration and profile management | Mahbub Hasan | bar: Week 14
30 | CRUD for hospital equipment and test services | Mujtahid Tabassum | bar: Week 15
31 | Manage patient requests (accept/reject system) | Tauhidul Islam | bar: Week 16
32 | Develop hospital–doctor linking | MD. Zobayer Hosen | bar: Week 16
33 | Review and test hospital module features | Mahbub Hasan | bar: Week 16 to Week 17
34 | Implement admin login and authentication | Mujtahid Tabassum | bar: Week 18
35 | Manage users (patients, doctors, hospitals) | Tauhidul Islam | bar: Week 18
36 | Add reporting & graphs dashboard | MD. Zobayer Hosen | bar: Week 18 to Week 19
37 | Implement audit logs and monitoring | Mahbub Hasan | bar: Week 19 to Week 20
38 | Develop symptom input form (NLP interface) | Mujtahid Tabassum | bar: Week 20 to Week 21
39 | Train/integrate AI model for basic diagnosis suggestions | Tauhidul Islam | bar: Week 21
40 | Test AI responses for accuracy & safety | MD. Zobayer Hosen | bar: Week 13 to Week 14
41 | Unit testing for all modules | Mahbub Hasan | bar: Week 21
42 | Integration testing (patient–doctor–hospital flow) | Mujtahid Tabassum | bar: Week 22
43 | User Acceptance Testing (UAT) with stakeholders | Tauhidul Islam | bar: Week 14
44 | Bug fixing and retesting | MD. Zobayer Hosen | bar: Week 23
45 | Deploy system to cloud/hosting server (CI/CD setup) | Mahbub Hasan | bar: Week 21
46 | Publish app (mobile/web) and provide user documentation | Mujtahid Tabassum | bar: Week 16 to Week 17
47 | Plan maintenance, updates, and future scalability | Tauhidul Islam | bar: Week 24