## Sheet1
Serial | Role | Task Name | Planned Efford | Completed | Actual Efford
1 | Patient | Splash Screen | 2 | Yes | 2
2 |  | Swipe Animation with Information with carousel effect for first time open | 2 | Yes | 2
3 |  | Login or signup | 2 | Yes | 3
4 |  | upload profile picture | 1 | Yes | 1
5 |  | User must fill up basic information | 3 | Yes | 2 | BAC | 142
6 |  | User need to allow the permission of location or manually select the co-ordinate of location from maps | 3 | Yes | 3 | BCWS | 76
7 |  | Search bar with filtering option | 3 | Yes | 3 | BCWP | 61
8 |  | Most popular hospital lists on carousel effect | 3 | Yes | 4 | ACWP | 63
9 |  | Favorite items on carousel effect | 4 | Yes | 2
10 |  | List of all available services | 3 | Yes | 3
11 |  | Home Screen icon | 4 | Yes | 4 | SPI | 0.80263
12 |  | Medicine Reminder icon | 5 | Yes | 5 | SV | -15
13 |  | Blog Page Icon | 2 | Yes | 2 | CPI | 0.96825
14 |  | AI Doctor | 3 | Yes | 4 | CV | -2
15 |  | User profile page | 4 | Yes | 3
16 |  | Order History menu | 3 | Yes | 4 | Sechdule for Completetion | 53.5211 | %
17 |  | Track Appointment | 2 | Yes | 3 | Complete | 42.9577 | %
18 |  | Active Orders (Booked Cabin, oxygen cylinder, ambulance etc.) | 3 | Yes | 4
19 |  | All the page that has been opened from another page, will be pushed to stack of history | 2 | Yes | 3
20 |  | Support mobile banking, card and pay cash by hand option (for limited services like appoinment) | 2 | Yes | 2
21 |  | Can comment and rating to doctor and hospital | 5 | Yes | 4
22 |  | Can read all the essential information of hospital and doctor like age, degrees, availability, location, gender, age, name, ratings, comments etc. | 4 | No
23 | Admin | Can read history of everything | 3 | No
24 |  | Can Create, read, update and delete accounts, credentials, reports. | 3 | No
25 |  | Can create, read, update and delete new moderators | 2 | No
26 |  | Can change username, password | 3 | No
27 | Hospital | Basic Information | 4 | No
28 |  | Can see most recent comments with view all options | 4 | No
29 |  | Can see list of serial appointed by patient with view all options | 3 | No
30 |  | Welcome Page | 2 | No
31 |  | Account Options | 3 | No
32 |  | Reviews | 4 | No
33 |  | Blog page | 3 | No
34 |  | Can see and create read update and delete doctor lists | 3 | No
35 |  | Can see the requested list of doctor queued for approve | 2 | No
36 |  | Cabin section where all the cabin related things will maintains | 3 | No
37 |  | All track list of equipents | 4 | No
38 |  | Track list of ambulance | 2 | No
39 |  | Section for handling users queries | 3 | No
40 | Doctor | Basic Information | 3 | No
41 |  | Can see most recent comments with view all options | 3 | No
42 |  | Can see list of serial appointed by patient with view all options | 3 | No
43 |  | Welcome Page | 4 | No
44 |  | Account Options | 2 | No
45 |  | Reviews | 3 | No
46 |  | Blog page | 5 | No
47 |  | Histoy of patient | 3 | No
142