## Sheet1
Serial No. | Task Name | User Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1 | Splash Screen | Mahbub Hasan | bar: W1
2 | Swipe Animation with Information carousel | Mujtahid Tabassum | bar: W1
3 | Login or signup | MD. Zobayer Hosen | bar: W1
4 | Upload profile picture | Tauhidul Islam | bar: W2
5 | User must fill up basic information | Mujtahid Tabassum | bar: W2
6 | User need to allow permission of location | Mahbub Hasan | bar: W5
7 | Search bar with filtering option | Tauhidul Islam | bar: W7
8 | Most popular hospital lists on carousel | MD. Zobayer Hosen | bar: W8
9 | Favorite items on carousel effect | Mujtahid Tabassum | bar: W8
10 | List of all available services | Mahbub Hasan | bar: W8
11 | Home Screen icon | Tauhidul Islam | bar: W3
12 | Medicine Reminder icon | MD. Zobayer Hosen | bar: W3
13 | Blog Page Icon | Mahbub Hasan | bar: W4
14 | AI Doctor | Mujtahid Tabassum | bar: W8
15 | User profile page | Tauhidul Islam | bar: W6 to W8
16 | Order History menu | MD. Zobayer Hosen | bar: W9
17 | Track Appointment | Mahbub Hasan | bar: W9
18 | Active Orders (Booked Cabin, oxygen, ambulance) | Mujtahid Tabassum | bar: W10
19 | Navigation history stack | Tauhidul Islam | bar: W10
20 | Payment integration (mobile banking, card, cash) | MD. Zobayer Hosen | bar: W11 to W12
21 | Comment and rating to doctor and hospital | Mahbub Hasan | bar: W12
22 | Read hospital and doctor information | Mujtahid Tabassum | bar: W13
23 | Can read history of everything | Tauhidul Islam | bar: W13 to W14
24 | CRUD accounts, credentials, reports | MD. Zobayer Hosen | bar: W14 to W16
25 | Create, read, update, delete moderators | Mahbub Hasan | bar: W16 to W17
26 | Can change username, password | Mujtahid Tabassum | bar: W13 to W14
27 | Basic Information | Tauhidul Islam | bar: W13 to W14
28 | Can see most recent comments with view all | MD. Zobayer Hosen | bar: W13 to W14
29 | Can see list of serial appointed by patient | Mahbub Hasan | bar: W14
30 | Welcome Page | Mujtahid Tabassum | bar: W15
31 | Account Options | Tauhidul Islam | bar: W16
32 | Reviews | MD. Zobayer Hosen | bar: W16
33 | Blog page | Mahbub Hasan | bar: W16 to W17
34 | CRUD doctor lists | Mujtahid Tabassum | bar: W18
35 | Can see requested list of doctor for approve | Tauhidul Islam | bar: W18
36 | Cabin section management | MD. Zobayer Hosen | bar: W18 to W19
37 | All track list of equipments | Mahbub Hasan | bar: W19 to W20
38 | Track list of ambulance | Mujtahid Tabassum | bar: W20 to W21
39 | Section for handling users queries | Tauhidul Islam | bar: W21
40 | Basic Information | MD. Zobayer Hosen | bar: W13 to W14
41 | Can see most recent comments with view all | Mahbub Hasan | bar: W21
42 | Can see list of serial appointed by patient | Mujtahid Tabassum | bar: W22
43 | Welcome Page | Tauhidul Islam | bar: W14
44 | Account Options | MD. Zobayer Hosen | bar: W23
45 | Reviews | Mahbub Hasan | bar: W21
46 | Blog page | Mujtahid Tabassum | bar: W16 to W17
47 | History of patient | Tauhidul Islam | bar: W24