## Sheet1
Serial No. | Task Name | User Type | Phase | Duration (week) | Start Week | End Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1 | Splash Screen | Patient | Phase 1 | 1 | 1 | 1 | bar: W1 to W26
2 | Swipe Animation with Information carousel | Patient | Phase 1 | 1 | 1 | 1 | bar: W1 to W26
3 | Login or signup | Patient | Phase 1 | 1 | 1 | 1 | bar: W1 to W26
4 | Upload profile picture | Patient | Phase 1 | 1 | 2 | 2 | bar: W1 to W26
5 | User must fill up basic information | Patient | Phase 1 | 1 | 2 | 2 | bar: W1 to W26
6 | User need to allow permission of location | Patient | Phase 1 | 1 | 5 | 5 | bar: W1 to W26
7 | Search bar with filtering option | Patient | Phase 2 | 2 | 6 | 6 | bar: W1 to W26
8 | Most popular hospital lists on carousel | Patient | Phase 2 | 1 | 7 | 7 | bar: W1 to W26
9 | Favorite items on carousel effect | Patient | Phase 2 | 1 | 7 | 7 | bar: W1 to W26
10 | List of all available services | Patient | Phase 2 | 1 | 7 | 7 | bar: W1 to W26
11 | Home Screen icon | Patient | Phase 2 | 1 | 3 | 3 | bar: W1 to W26
12 | Medicine Reminder icon | Patient | Phase 2 | 1 | 3 | 3 | bar: W1 to W26
13 | Blog Page Icon | Patient | Phase 2 | 1 | 4 | 4 | bar: W1 to W26
14 | AI Doctor | Patient | Phase 2 | 1 | 8 | 8 | bar: W1 to W26
15 | User profile page | Patient | Phase 3 | 3 | 5 | 8 | bar: W1 to W26
16 | Order History menu | Patient | Phase 3 | 1 | 9 | 9 | bar: W1 to W26
17 | Track Appointment | Patient | Phase 3 | 1 | 9 | 9 | bar: W1 to W26
18 | Active Orders (Booked Cabin, oxygen, ambulance) | Patient | Phase 3 | 1 | 10 | 10 | bar: W1 to W26
19 | Navigation history stack | Patient | Phase 3 | 1 | 10 | 10 | bar: W1 to W26
20 | Payment integration (mobile banking, card, cash) | Patient | Phase 3 | 2 | 11 | 12 | bar: W1 to W26
21 | Comment and rating to doctor and hospital | Patient | Phase 3 | 1 | 12 | 12 | bar: W1 to W26
22 | Read hospital and doctor information | Patient | Phase 3 | 1 | 13 | 13 | bar: W1 to W26
23 | Can read history of everything | Admin | Phase 4 | 2 | 13 | 14 | bar: W1 to W26
24 | CRUD accounts, credentials, reports | Admin | Phase 4 | 3 | 14 | 16 | bar: W1 to W26
25 | Create, read, update, delete moderators | Admin | Phase 4 | 2 | 16 | 17 | bar: W1 to W26
26 | Can change username, password | Admin | Phase 4 | 1 | 13 | 3 | bar: W1 to W26
27 | Basic Information | Hospital | Phase 4 | 2 | 13 | 14 | bar: W1 to W26
28 | Can see most recent comments with view all | Hospital | Phase 4 | 2 | 13 | 14 | bar: W1 to W26
29 | Can see list of serial appointed by patient | Hospital | Phase 4 | 2 | 14 | 14 | bar: W1 to W26
30 | Welcome Page | Hospital | Phase 4 | 1 | 14 | 14 | bar: W1 to W26
31 | Account Options | Hospital | Phase 4 | 1 | 15 | 15 | bar: W1 to W26
32 | Reviews | Hospital | Phase 4 | 1 | 15 | 15 | bar: W1 to W26
33 | Blog page | Hospital | Phase 4 | 2 | 16 | 17 | bar: W1 to W26
34 | CRUD doctor lists | Hospital | Phase 4 | 1 | 18 | 18 | bar: W1 to W26
35 | Can see requested list of doctor for approve | Hospital | Phase 4 | 1 | 18 | 18 | bar: W1 to W26
36 | Cabin section management | Hospital | Phase 4 | 2 | 18 | 19 | bar: W1 to W26
37 | All track list of equipments | Hospital | Phase 4 | 2 | 19 | 20 | bar: W1 to W26
38 | Track list of ambulance | Hospital | Phase 4 | 2 | 20 | 21 | bar: W1 to W26
39 | Section for handling users queries | Hospital | Phase 4 | 1 | 21 | 21 | bar: W1 to W26
40 | Basic Information | Doctor | Phase 4 | 2 | 13 | 14 | bar: W1 to W26
41 | Can see most recent comments with view all | Doctor | Phase 4 | 1 | 21 | 21 | bar: W1 to W26
42 | Can see list of serial appointed by patient | Doctor | Phase 4 | 1 | 22 | 22 | bar: W1 to W26
43 | Welcome Page | Doctor | Phase 4 | 1 | 14 | 14 | bar: W1 to W26
44 | Account Options | Doctor | Phase 4 | 1 | 23 | 23 | bar: W1 to W26
45 | Reviews | Doctor | Phase 4 | 1 | 21 | 21 | bar: W1 to W26
46 | Blog page | Doctor | Phase 4 | 2 | 16 | 17 | bar: W1 to W26
47 | History of patient | Doctor | Phase 4 | 1 | 24 | 24 | bar: W1 to W26